## Marketing Plan
The Story of Glen Mor Marketing Plan
From bush to toast: showing the journey of the Glen Mor raspberry
Phase | Activity | What it involves | Owner | Timing | Status
1. Research & Story | Research the story | Gather the origin and history of the Glen Mor raspberry — records, background and key facts. | Jan | May | Complete
1. Research & Story | Talk to breeders & licensing | Meet the breeding team and the licensing team to confirm facts, permissions and any sign-off needed. | Jan | May | Complete
1. Research & Story | Create draft 'story' | Write the first draft narrative of the Glen Mor journey to shape all later content. | Jan | May | Complete
2. Collaboration | Instigate preserver collaboration | Reach out to preservers and set up the partnership (incl. Naomi) for the preserving side of the story. | Jan and Hannah | June | Complete
2. Collaboration | Collaboration meeting | Kick-off meeting to align on roles, content capture and timelines for the campaign. | Jan and Hannah | June | Complete
3. Showcase | Showcase at Fruit for the Future | Feature the Glen Mor raspberry at the event and capture live material for the campaign. | Jan and Hannah | July | Complete
3. Showcase | Curate 'bush to toast' content | Collect images and video from our side and Naomi's preserving side across the full journey. | Jan and Hannah | July | In Progress
4. Content & Delivery | Create storyboard (A3 & A5) | Design the story boards A3 for display and A5 as an engaging explainer to accompany the jam. | Jan | August | Complete
4. Content & Delivery | Send jam to stakeholders & press | Post finished jam to external stakeholders and press with the A5 story board. | Hannah | Aug – Oct | Not started
4. Content & Delivery | Publish Instagram reels | Release short-form reels telling the journey from bush to toast. | Hannah | Aug – Oct | Not started
4. Content & Delivery | Publish LinkedIn carousel | Share the story as a LinkedIn carousel for a professional / trade audience. | Hannah | Aug – Oct | Not started
4. Content & Delivery | Publish journey video | Release the full 'bush to toast' journey video across channels. | Hannah | Aug – Oct | Not started
Status summary
| Not started | 4
| In progress | 1
| Complete | 7

## Timeline
Story of Glen Mor — Timeline at a glance
Activity | May | Jun | Jul | Aug | Sep | Oct
Research the story | bar: May
Talk to breeders & licensing | bar: May
Create draft story | bar: May
Preserver collaboration | bar: Jun
Collaboration meeting | bar: Jun
Fruit for the Future showcase | bar: Jul
Curate 'bush to toast' content | bar: Jul to Aug
Storyboard (A3 & A5) | bar: Aug
Jam to stakeholders & press | bar: Aug to Oct
Instagram reels | bar: Aug to Oct
LinkedIn carousel | bar: Aug to Oct
Journey video | bar: Aug to Oct
Phases:
Research & Story
Collaboration
Showcase
Content & Delivery