## Content Map
# | Old URL | Page type | Suggested action | Agreed action | Working action | Notes | 12m clicks (GSC) | 12m views (GA4) | New URL | Owner | Claire sign-off | Status | Redirect set up
1 | https://www.lipid.co.uk/ | Landing page | Rewrite |  | Rewrite | Becomes the MLA landing page in the Hutton structure. Rebuild from the Hutton template. | 257 | 2698 |  |  |  | Not started | No
2 | https://www.lipid.co.uk/about-us | Information page | Rewrite |  | Rewrite | Core page. Rewrite for Hutton tone and merge in company history. | 43 | 274 |  |  |  | Not started | No
3 | https://www.lipid.co.uk/james-hutton-limited | Information page | Retire |  | Retire | Fold into the About page or the Hutton corporate pages. | 7 | 67 |  |  |  | Not started | No
4 | https://www.lipid.co.uk/quality | Information page | Rewrite |  | Rewrite | Key trust page (accreditations, proficiency testing). Claire to check accuracy. | 1 | 137 |  |  |  | Not started | No
5 | https://www.lipid.co.uk/samples | Information page | Rewrite |  | Rewrite | Sample submission guidance is high value. Check downloads and forms attached. | 1 | 118 |  |  |  | Not started | No
6 | https://www.lipid.co.uk/services/lipid-analysis/meet-team | Information page | Merge |  | Merge | Merge into the team or About section. | 1 | 62 |  |  |  | Not started | No
7 | https://www.lipid.co.uk/testimonials | Information page | Rewrite |  | Rewrite | Merge in the testimonials carousel slide. Check permission to keep quotes. | 4 | 73 |  |  |  | Not started | No
8 | https://www.lipid.co.uk/useful-links | Information page | Retire |  | Retire | Check links still work and whether Hutton would host a links page at all. | 0 | 46 |  |  |  | Not started | No
9 | https://www.lipid.co.uk/services | Service page | Rewrite |  | Rewrite | Core commercial page. Prioritise. | 4 | 372 |  |  |  | Not started | No
10 | https://www.lipid.co.uk/services/analyses | Service page | Rewrite |  | Rewrite | Core commercial page. Prioritise. | 16 | 227 |  |  |  | Not started | No
11 | https://www.lipid.co.uk/services/method-development-validation | Service page | Rewrite |  | Rewrite | Core commercial page. Prioritise. | 2 | 65 |  |  |  | Not started | No
12 | https://www.lipid.co.uk/services/stability | Service page | Rewrite |  | Rewrite | Suggested pilot page: representative, commercial and easy to review. | 2 | 31 |  |  |  | Not started | No
13 | https://www.lipid.co.uk/sectors | Sector page | Rewrite |  | Rewrite | Sector landing page. Rebuild from the Hutton template. | 1 | 211 |  |  |  | Not started | No
14 | https://www.lipid.co.uk/sectors/biofuel-analysis | Sector page | Rewrite |  | Rewrite | Commercial page by sector. Rewrite for Hutton structure and check keywords. | 2 | 54 |  |  |  | Not started | No
15 | https://www.lipid.co.uk/sectors/clinical-samples | Sector page | Rewrite |  | Rewrite | Commercial page by sector. Rewrite for Hutton structure and check keywords. | 3 | 66 |  |  |  | Not started | No
16 | https://www.lipid.co.uk/sectors/food-drink | Sector page | Rewrite |  | Rewrite | Commercial page by sector. Rewrite for Hutton structure and check keywords. | 0 | 55 |  |  |  | Not started | No
17 | https://www.lipid.co.uk/sectors/nutraceuticals | Sector page | Rewrite |  | Rewrite | Commercial page by sector. Rewrite for Hutton structure and check keywords. | 1 | 48 |  |  |  | Not started | No
18 | https://www.lipid.co.uk/sectors/oil-content-and-oil-seed | Sector page | Rewrite |  | Rewrite | Commercial page by sector. Rewrite for Hutton structure and check keywords. | 4 | 60 |  |  |  | Not started | No
19 | https://www.lipid.co.uk/sectors/skin-lipids-and-skin-health | Sector page | Rewrite |  | Rewrite | Commercial page by sector. Rewrite for Hutton structure and check keywords. | 0 | 47 |  |  |  | Not started | No
20 | https://www.lipid.co.uk/case-studies | Case study | Rewrite |  | Rewrite | Landing page for case studies. Rebuild in Hutton format. | 0 | 3 |  |  |  | Not started | No
21 | https://www.lipid.co.uk/case-studies/omtrygtm-analysis-api-fpp | Case study | Migrate as is |  | Migrate as is | Proof point for services. Light edit only. | 3 | 37 |  |  |  | Not started | No
22 | https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-10/Customer Form Oct 2018.pdf | Download / white paper | Rewrite |  | Rewrite | Not in the original URL list. Dated 2018. Check for a current version and replace. | 0 | 0 |  |  |  | Not started | No
23 | https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-10/GMP 34058 120515 Human.pdf | Download / white paper | Retire |  | Retire | Not in the original URL list. Looks like a GMP document. Claire to confirm it is current. | 0 | 0 |  |  |  | Not started | No
24 | https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-10/GMP 34058 120515 Veterinary.pdf | Download / white paper | Retire |  | Retire | Not in the original URL list. Looks like a GMP document. Claire to confirm it is current. | 0 | 0 |  |  |  | Not started | No
25 | https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-10/JHL - Website Privacy Notice.FINAL_.V2.May2018.pdf | Download / white paper | Retire |  | Retire | Not in the original URL list. Use the main Hutton privacy notice and redirect to it. | 0 | 0 |  |  |  | Not started | No
26 | https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-10/Sample Submission Form Oct 2018.pdf | Download / white paper | Rewrite |  | Rewrite | Not in the original URL list. Dated 2018. Check for a current version and replace. | 1 | 0 |  |  |  | Not started | No
27 | https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-12/Mallakin RLO paper - 2018.pdf | Download / white paper | Retire |  | Retire | Not in the original URL list. PDF paper with search clicks. Check permission to host it, then keep or link out. | 17 | 0 |  |  |  | Not started | No
28 | https://www.lipid.co.uk/white-papers/white-paper-1 | Download / white paper | Migrate as is |  | Migrate as is | Lead generation asset. Check the file and any gated form. | 5 | 49 |  |  |  | Not started | No
29 | https://www.lipid.co.uk/bill-christie | Person profile | Merge |  | Merge | High traffic (see /bill-christie-0). Consolidate into one page and redirect this URL to it. | 39 | 73 |  |  |  | Not started | No
30 | https://www.lipid.co.uk/bill-christie-0 | Person profile | Merge |  | Merge | High traffic. This and /bill-christie together bring more clicks than any page except the homepage, while /people/william-christie gets almost none. Consolidate into ONE strong page and redirect both. | 72 | 106 |  |  |  | Not started | No
31 | https://www.lipid.co.uk/charlie-scrimgeour | Person profile | Retire |  | Retire | Some search traffic. Consolidate with /people/charlie-scrimgeour and redirect. | 5 | 21 |  |  |  | Not started | No
32 | https://www.lipid.co.uk/claire-traynor | Person profile | Merge |  | Merge | Meaningful search traffic. Consolidate with /people/claire-traynor and redirect. | 20 | 25 |  |  |  | Not started | No
33 | https://www.lipid.co.uk/people/allan-dick | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 4 | 12 |  |  |  | Not started | No
34 | https://www.lipid.co.uk/people/andrew-kindness | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
35 | https://www.lipid.co.uk/people/angus-wilson | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
36 | https://www.lipid.co.uk/people/charlie-scrimgeour | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
37 | https://www.lipid.co.uk/people/christine-branney | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 1 |  |  |  | Not started | No
38 | https://www.lipid.co.uk/people/claire-fernie | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
39 | https://www.lipid.co.uk/people/claire-traynor | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 5 |  |  |  | Not started | No
40 | https://www.lipid.co.uk/people/demi-elliot | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 3 |  |  |  | Not started | No
41 | https://www.lipid.co.uk/people/dr-carol-ann-craig | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
42 | https://www.lipid.co.uk/people/dr-gary-dobson | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 1 | 1 |  |  |  | Not started | No
43 | https://www.lipid.co.uk/people/dr-rob-winwood | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 6 | 9 |  |  |  | Not started | No
44 | https://www.lipid.co.uk/people/finlay-stewart | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 1 |  |  |  | Not started | No
45 | https://www.lipid.co.uk/people/gordon-mcdougall | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
46 | https://www.lipid.co.uk/people/jean-wilkie | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
47 | https://www.lipid.co.uk/people/jennifer-haig | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
48 | https://www.lipid.co.uk/people/julie-sungurtas | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 1 | 0 |  |  |  | Not started | No
49 | https://www.lipid.co.uk/people/kenneth-amayo | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
50 | https://www.lipid.co.uk/people/kirsty-macleod | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
51 | https://www.lipid.co.uk/people/lucy-asare | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 1 |  |  |  | Not started | No
52 | https://www.lipid.co.uk/people/professor-terry-k-smith | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 1 |  |  |  | Not started | No
53 | https://www.lipid.co.uk/people/sophie-craig | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 1 |  |  |  | Not started | No
54 | https://www.lipid.co.uk/people/stuart-ramage | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
55 | https://www.lipid.co.uk/people/thomas-taylor | Person profile | Rewrite |  | Rewrite | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
56 | https://www.lipid.co.uk/people/william-christie | Person profile | Retire |  | Retire | Confirm the person is still at MLA and match the Hutton people-page format. | 0 | 0 |  |  |  | Not started | No
57 | https://www.lipid.co.uk/news | News article | Rewrite |  | Rewrite | News landing page. Depends on the Hutton news structure. | 0 | 276 |  |  |  | Not started | No
58 | https://www.lipid.co.uk/news/25-years-our-story-so-far | News article | Merge |  | Merge | Company history. Merge into the About page. | 2 | 10 |  |  |  | Not started | No
59 | https://www.lipid.co.uk/news/analytical-chemist-vacancy-1 | News article | Retire |  | Retire | Old vacancy. Retire. | 2 | 4 |  |  |  | Not started | No
60 | https://www.lipid.co.uk/news/another-successful-course-mylnefield-lipid-analysis | News article | Retire |  | Retire | Past course report. Retire unless the course continues. | 4 | 7 |  |  |  | Not started | No
61 | https://www.lipid.co.uk/news/cannabidiol-safe-daily-dose-limit-cut-food-regulator | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 0 | 27 |  |  |  | Not started | No
62 | https://www.lipid.co.uk/news/dietary-high-oleic-acid-soybean-oil-dose-dependently-attenuates-egg-yolk-content-n-3 | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 1 | 8 |  |  |  | Not started | No
63 | https://www.lipid.co.uk/news/egg-centric-nutrition-humans | News article | Migrate as is |  | Migrate as is | Very high search visibility (17,000+ impressions). Keep and migrate carefully. | 37 | 73 |  |  |  | Not started | No
64 | https://www.lipid.co.uk/news/eu-amendments-heavy-metals-go-effect | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 0 | 38 |  |  |  | Not started | No
65 | https://www.lipid.co.uk/news/gmp-stability-storage-and-testing | News article | Migrate as is |  | Migrate as is | Supports the stability service. Check traffic. | 1 | 7 |  |  |  | Not started | No
66 | https://www.lipid.co.uk/news/goed-study-puts-rest-toxicity-concerns | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 0 | 3 |  |  |  | Not started | No
67 | https://www.lipid.co.uk/news/heavy-metal-analysis-icp-ms | News article | Migrate as is |  | Migrate as is | Supports a service. Check traffic. | 9 | 16 |  |  |  | Not started | No
68 | https://www.lipid.co.uk/news/important-information-regarding-prices-1st-april-2021 | News article | Retire |  | Retire | Dated price notice. Retire. | 0 | 14 |  |  |  | Not started | No
69 | https://www.lipid.co.uk/news/issfal-issues-new-guidelines-analysis-blood-status-clinical-research | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 1 | 8 |  |  |  | Not started | No
70 | https://www.lipid.co.uk/news/meet-our-newest-team-members | News article | Retire |  | Retire | Dated staff news. Retire once profiles are checked. | 1 | 9 |  |  |  | Not started | No
71 | https://www.lipid.co.uk/news/meet-team-claire-traynor-celebrating-25-years | News article | Merge |  | Merge | Merge into her profile or the history section. | 5 | 12 |  |  |  | Not started | No
72 | https://www.lipid.co.uk/news/mla-team-scores-perfect-zero-latest-proficiency-testing-cannabis-and-related-products | News article | Migrate as is |  | Migrate as is | Quality proof point. Could sit on the Quality page too. | 3 | 33 |  |  |  | Not started | No
73 | https://www.lipid.co.uk/news/mylnefield-lipid-analysis-claims-first-place-prestigious-proficiency-testing-programme | News article | Migrate as is |  | Migrate as is | Quality proof point. Could sit on the Quality page too. | 0 | 21 |  |  |  | Not started | No
74 | https://www.lipid.co.uk/news/mylnefield-lipid-analysis-work-study-characterising-ratfish-liver-oil | News article | Migrate as is |  | Migrate as is | Case-study style content. Check traffic. | 7 | 16 |  |  |  | Not started | No
75 | https://www.lipid.co.uk/news/new-anti-inflammatory-product-created-following-analysis-mylnefield-lipid-analysis | News article | Migrate as is |  | Migrate as is | Case-study style content. Check traffic. | 0 | 7 |  |  |  | Not started | No
76 | https://www.lipid.co.uk/news/new-database-msu-references-450-plant-fatty-acids | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 6 | 12 |  |  |  | Not started | No
77 | https://www.lipid.co.uk/news/new-paper-first-report-quality-and-purity-evaluations-avocado-oil-sold-us | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 0 | 4 |  |  |  | Not started | No
78 | https://www.lipid.co.uk/news/new-study-shows-clear-benefit-increased-epa-dha-intake | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 0 | 2 |  |  |  | Not started | No
79 | https://www.lipid.co.uk/news/omega-3-fatty-acid-content-should-be-expressed-weight-not-area-percent-says-goed-industry | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 4 | 14 |  |  |  | Not started | No
80 | https://www.lipid.co.uk/news/open-business | News article | Retire |  | Retire | Dated operational notice. Retire. | 0 | 3 |  |  |  | Not started | No
81 | https://www.lipid.co.uk/news/oxidised-fish | News article | Merge |  | Merge | Near-duplicate of oxidised-fish-oil-problem but with real search visibility. Merge and redirect. | 11 | 31 |  |  |  | Not started | No
82 | https://www.lipid.co.uk/news/oxidised-fish-oil-problem | News article | Migrate as is |  | Migrate as is | Own expertise, likely SEO value. Check traffic. | 23 | 100 |  |  |  | Not started | No
83 | https://www.lipid.co.uk/news/professor-frank-d-gunstone | News article | Migrate as is |  | Migrate as is | Attracts search clicks. Keep, ideally with light edits. | 13 | 28 |  |  |  | Not started | No
84 | https://www.lipid.co.uk/news/reduce-it-study | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 0 | 2 |  |  |  | Not started | No
85 | https://www.lipid.co.uk/news/research-article-encapsulated-fish-oil-products-available-uk-meet-regulatory-guidelines | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 1 | 5 |  |  |  | Not started | No
86 | https://www.lipid.co.uk/news/residual-solvents-analysis | News article | Migrate as is |  | Migrate as is | Supports a service. Check traffic. | 5 | 21 |  |  |  | Not started | No
87 | https://www.lipid.co.uk/news/rob-winwood-can-sterols-and-stanols-be-beneficial-heart-health-and-how-do-i-find-out-how-much | News article | Migrate as is |  | Migrate as is | Expert blog. Check traffic. | 1 | 9 |  |  |  | Not started | No
88 | https://www.lipid.co.uk/news/rob-winwood-joins-consultant | News article | Retire |  | Retire | Dated staff news. Covered by his profile page. | 4 | 18 |  |  |  | Not started | No
89 | https://www.lipid.co.uk/news/scotlands-life-sciences-awards-2019-call-nominations-now-open | News article | Retire |  | Retire | Dated call for nominations. Retire. | 0 | 3 |  |  |  | Not started | No
90 | https://www.lipid.co.uk/news/statement-graham-ogg-0 | News article | Retire |  | Retire | Duplicate of a slide and an earlier statement. Retire or check with Ian. | 5 | 17 |  |  |  | Not started | No
91 | https://www.lipid.co.uk/news/thought-provoking-paper-bmj-potential-effect-food-emulsifiers-cardiovascular-diseases-cvd | News article | Retire |  | Retire | Third-party or industry news. Decide on traffic and shelf life. | 0 | 17 |  |  |  | Not started | No
92 | https://www.lipid.co.uk/news/we-are-members-goed | News article | Merge |  | Merge | Membership. Merge into the Quality or About page. | 1 | 16 |  |  |  | Not started | No
93 | https://www.lipid.co.uk/news/were-exhibiting-issfal-congress | News article | Retire |  | Retire | Past event announcement. Retire. | 0 | 5 |  |  |  | Not started | No
94 | https://www.lipid.co.uk/news/wishing-sheena-happy-retirement | News article | Retire |  | Retire | Dated staff news. Retire. | 2 | 3 |  |  |  | Not started | No
95 | https://www.lipid.co.uk/events | Event / course | Retire |  | Retire | Decide whether events sit on Hutton events pages instead. | 0 | 26 |  |  |  | Not started | No
96 | https://www.lipid.co.uk/events/issfal-2020 | Event / course | Retire |  | Retire | Past event. Redirect to the events landing page. | 0 | 0 |  |  |  | Not started | No
97 | https://www.lipid.co.uk/events/webinar-lipid-classes-compounds-quality-control-and-contaminants | Event / course | Retire |  | Retire | Keep if the recording is still available, otherwise retire. | 0 | 1 |  |  |  | Not started | No
98 | https://www.lipid.co.uk/register-fatty-acids-lipids-analysis-course | Event / course | Retire |  | Retire | Is the course still running? If not, retire. | 1 | 3 |  |  |  | Not started | No
99 | https://www.lipid.co.uk/services/training-course | Event / course | Retire |  | Retire | Not in the original URL list. Gets search clicks. Confirm the course still runs, and align with the course registration page. | 23 | 76 |  |  |  | Not started | No
100 | https://www.lipid.co.uk/25th-anniversary-videos | Media | Merge |  | Merge | Merge with the videos page or the company history section. | 0 | 3 |  |  |  | Not started | No
101 | https://www.lipid.co.uk/videos | Media | Retire |  | Retire | Decide whether videos are embedded on service pages or kept as a hub. | 1 | 2 |  |  |  | Not started | No
102 | https://www.lipid.co.uk/contact-us | Contact / form | Rewrite |  | Rewrite | Check where enquiry emails and form submissions go before launch. | 11 | 224 |  |  |  | Not started | No
103 | https://www.lipid.co.uk/form/contact/confirmation | Contact / form | Rewrite |  | Rewrite | Not in the original URL list. Thank-you page after the contact form. Replicate on the Hutton form so conversion tracking still works. | 0 | 32 |  |  |  | Not started | No
104 | https://www.lipid.co.uk/new-customer-form | Contact / form | Rewrite |  | Rewrite | Not in the original URL list. One of the most-viewed pages with long engagement. Check where submissions go and rebuild carefully. | 0 | 176 |  |  |  | Not started | No
105 | https://www.lipid.co.uk/subscribe | Contact / form | Retire |  | Retire | Mailing list sign-up. Check which tool holds the list and GDPR consent before moving. | 0 | 1 |  |  |  | Not started | No
106 | https://www.lipid.co.uk/slides/celebrating-25-years | Homepage slide | Retire |  | Retire | Homepage carousel slide, not a standalone page. Recreate as a banner if wanted. | 0 | 0 |  |  |  | Not started | No
107 | https://www.lipid.co.uk/slides/latest-blog-egg-centric-nutrition-humans | Homepage slide | Retire |  | Retire | Homepage carousel slide, not a standalone page. Recreate as a banner if wanted. | 0 | 0 |  |  |  | Not started | No
108 | https://www.lipid.co.uk/slides/latest-blog-oxidised-fish-oil-problem | Homepage slide | Retire |  | Retire | Homepage carousel slide, not a standalone page. Recreate as a banner if wanted. | 0 | 0 |  |  |  | Not started | No
109 | https://www.lipid.co.uk/slides/mla-team-scores-perfect-zero | Homepage slide | Retire |  | Retire | Homepage carousel slide, not a standalone page. Recreate as a banner if wanted. | 0 | 0 |  |  |  | Not started | No
110 | https://www.lipid.co.uk/slides/mylnefield-lipid-analysis | Homepage slide | Retire |  | Retire | Homepage carousel slide, not a standalone page. Recreate as a banner if wanted. | 0 | 2 |  |  |  | Not started | No
111 | https://www.lipid.co.uk/slides/new-service-cannabinoid-profiling | Homepage slide | Rewrite |  | Rewrite | This will become the Cannabis Analysis page (HCA) | 0 | 0 |  |  |  | Not started | No
112 | https://www.lipid.co.uk/slides/our-laboratory-open | Homepage slide | Retire |  | Retire | Homepage carousel slide, not a standalone page. Recreate as a banner if wanted. | 0 | 0 |  |  |  | Not started | No
113 | https://www.lipid.co.uk/slides/rob-winwood-latest-blog | Homepage slide | Retire |  | Retire | Homepage carousel slide, not a standalone page. Recreate as a banner if wanted. | 0 | 0 |  |  |  | Not started | No
114 | https://www.lipid.co.uk/slides/statement-graham-ogg | Homepage slide | Retire |  | Retire | Homepage carousel slide, not a standalone page. Recreate as a banner if wanted. | 0 | 0 |  |  |  | Not started | No
115 | https://www.lipid.co.uk/slides/testimonials | Homepage slide | Merge |  | Merge | Merge into the testimonials page. | 0 | 0 |  |  |  | Not started | No
116 | https://www.lipid.co.uk/slides/we-are-members-goed | Homepage slide | Retire |  | Retire | Homepage carousel slide, not a standalone page. Recreate as a banner if wanted. | 0 | 0 |  |  |  | Not started | No
117 | https://www.lipid.co.uk/about-website | Legal / policy | Retire |  | Retire | Site info page. Hutton has its own site notices, so redirect there. | 0 | 27 |  |  |  | Not started | No
118 | https://www.lipid.co.uk/cookie-policy | Legal / policy | Retire |  | Retire | Use the main Hutton cookie policy and redirect to it. | 0 | 26 |  |  |  | Not started | No
119 | https://www.lipid.co.uk/freedom-information | Legal / policy | Retire |  | Retire | Check Hutton has an equivalent FOI page, then redirect to it. | 0 | 0 |  |  |  | Not started | No
120 | https://www.lipid.co.uk/node/3 | Test / duplicate | Retire |  | Retire | Raw Drupal node URL. Find out which page this resolves to. Probably a duplicate. | 0 | 0 |  |  |  | Not started | No
121 | https://www.lipid.co.uk/node/604 | Test / duplicate | Retire |  | Retire | Not in the original URL list. Raw node URL with views. Find out what it is. | 0 | 11 |  |  |  | Not started | No
122 | https://www.lipid.co.uk/node/724 | Test / duplicate | Retire |  | Retire | Raw Drupal node URL. Find out which page this resolves to. Probably a duplicate. | 0 | 0 |  |  |  | Not started | No
123 | https://www.lipid.co.uk/node/739 | Test / duplicate | Retire |  | Retire | Raw Drupal node URL. Find out which page this resolves to. Probably a duplicate. | 0 | 0 |  |  |  | Not started | No
124 | https://www.lipid.co.uk/node/761 | Test / duplicate | Retire |  | Retire | Not in the original URL list. Raw node URL with views. Find out what it is. | 0 | 16 |  |  |  | Not started | No
125 | https://www.lipid.co.uk/test-slide-page | Test / duplicate | Retire |  | Retire | Looks like a test page. Retire. | 0 | 0 |  |  |  | Not started | No

## Summary
MLA to Hutton migration: summary
All figures update automatically from the Content Map tab.
Total pages listed | 125
Actions agreed so far | 0
Agreed as % of pages | 0%
Working action | Pages | % of total
Migrate as is | 13 | 10.4%
Rewrite | 36 | 28.8%
Merge | 10 | 8%
Retire | 66 | 52.8%
Review | 0 | 0%
Total | 125 | 100%
Page type | Migrate as is | Rewrite | Merge | Retire | Review | Total
Landing page | 0 | 1 | 0 | 0 | 0 | 1
Information page | 0 | 4 | 1 | 2 | 0 | 7
Service page | 0 | 4 | 0 | 0 | 0 | 4
Sector page | 0 | 7 | 0 | 0 | 0 | 7
Case study | 1 | 1 | 0 | 0 | 0 | 2
Download / white paper | 1 | 2 | 0 | 4 | 0 | 7
Person profile | 0 | 12 | 3 | 13 | 0 | 28
News article | 11 | 1 | 4 | 22 | 0 | 38
Event / course | 0 | 0 | 0 | 5 | 0 | 5
Media | 0 | 0 | 1 | 1 | 0 | 2
Contact / form | 0 | 3 | 0 | 1 | 0 | 4
Homepage slide | 0 | 1 | 1 | 9 | 0 | 11
Legal / policy | 0 | 0 | 0 | 3 | 0 | 3
Test / duplicate | 0 | 0 | 0 | 6 | 0 | 6
Total | 13 | 36 | 10 | 66 | 0 | 125
Build progress | Pages | % of total
Not started | 125 | 100%
In progress | 0 | 0%
In review | 0 | 0%
Approved | 0 | 0%
Live | 0 | 0%
Claire sign-off complete | 0
Redirects set up | 0
Redirects as % of pages | 0%
Pages still to decide (Review) | 0
Traffic check | Pages | 12m clicks | 12m views
Migrate as is | 13 | 107 | 417
Rewrite | 36 | 357 | 5271
Merge | 10 | 151 | 338
Retire | 66 | 93 | 559
Review | 0 | 0 | 0
Total | 125 | 708 | 6585
Check the Retire and Review rows: any clicks there need a considered redirect.

## Guide
How to use this workbook
Where the suggestions came from | The suggested actions and notes are a first pass based on URL patterns and page titles only. I have not seen the page content or the traffic data, so please treat them as a starting point for Ian, Claire and you to confirm.
Pale yellow cells | These are the cells for you to fill in: Agreed action, New URL, Owner and Claire sign-off. Everything else is pre-filled or calculated.
Suggested vs agreed action | Column D is the suggestion. Choose from the dropdown in column E when a decision is made. Column F (Working action) shows the agreed action if there is one, otherwise the suggestion, and feeds the Summary tab.
Traffic columns | Clicks (Google Search Console) and views (GA4) are pulled in by formula from the GSC and GA4 tabs. Both cover 28 Sep 2025 to 28 Sep 2026 (GSC starts 26 Sep 2025). A zero means the page had no data in the export. To refresh, paste new exports over the GSC and GA4 tabs, keeping the same columns.
Pages added from analytics | Eleven rows were added because they appeared in GA4 or Search Console but were missing from the original URL list (forms, the training course page, PDFs and two raw node URLs). Their notes start with "Not in the original URL list".
Left out on purpose | Admin and system URLs (login, user pages, search, 403/404 pages), list pagination, image files and a few legacy .asp probes were left out as they need no rebuild. Ask whoever runs the server whether any legacy URLs need redirects.
Adding pages | Add new rows below the last one (the formulas, dropdowns and Summary counts run to row 150).
Migrate as is | Content moves across with light edits, rebuilt in the Hutton template.
Rewrite | Content needs reworking for the Hutton structure, tone or keywords.
Merge | Content folds into another page. Put the destination in the New URL column.
Retire | Page is not rebuilt. It still needs a 301 redirect to the closest relevant new page (never just the homepage).
Review | No decision yet. Check traffic and content, then decide.
Redirects | Every old URL should have a row with a New URL and "Yes" in the Redirect column before launch, including retired pages. Duplicates and raw /node/ URLs need redirects too.
Example row | Old URL: https://www.lipid.co.uk/services/stability ¦ Agreed action: Rewrite ¦ New URL: https://www.hutton.ac.uk/[agreed path]/stability ¦ Owner: Harvey ¦ Claire sign-off: Yes ¦ Status: Approved ¦ Redirect set up: No. (The path is a placeholder until the Hutton structure is agreed.)

## GSC
URL | Clicks (12m) | Impressions (12m)
https://www.lipid.co.uk/ | 257 | 5153
https://www.lipid.co.uk/bill-christie-0 | 72 | 1615
https://www.lipid.co.uk/about-us | 43 | 1670
https://www.lipid.co.uk/bill-christie | 39 | 1580
https://www.lipid.co.uk/news/egg-centric-nutrition-humans | 37 | 17824
https://www.lipid.co.uk/news/oxidised-fish-oil-problem | 23 | 8382
https://www.lipid.co.uk/services/training-course | 23 | 417
https://www.lipid.co.uk/claire-traynor | 20 | 447
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-12/Mallakin RLO paper - 2018.pdf | 17 | 1439
https://www.lipid.co.uk/services/analyses | 16 | 1388
https://www.lipid.co.uk/news/professor-frank-d-gunstone | 13 | 460
https://www.lipid.co.uk/news/oxidised-fish | 11 | 3574
https://www.lipid.co.uk/contact-us | 11 | 1280
https://www.lipid.co.uk/news/heavy-metal-analysis-icp-ms | 9 | 7397
https://www.lipid.co.uk/james-hutton-limited | 7 | 1508
https://www.lipid.co.uk/news/mylnefield-lipid-analysis-work-study-characterising-ratfish-liver-oil | 7 | 1281
https://www.lipid.co.uk/people/dr-rob-winwood | 6 | 141
https://www.lipid.co.uk/news/new-database-msu-references-450-plant-fatty-acids | 6 | 121
https://www.lipid.co.uk/news/residual-solvents-analysis | 5 | 1758
https://www.lipid.co.uk/white-papers/white-paper-1 | 5 | 982
https://www.lipid.co.uk/news/meet-team-claire-traynor-celebrating-25-years | 5 | 482
https://www.lipid.co.uk/charlie-scrimgeour | 5 | 144
https://www.lipid.co.uk/news/statement-graham-ogg-0 | 5 | 96
https://www.lipid.co.uk/services | 4 | 957
https://www.lipid.co.uk/news/omega-3-fatty-acid-content-should-be-expressed-weight-not-area-percent-says-goed-industry | 4 | 716
https://www.lipid.co.uk/testimonials | 4 | 463
https://www.lipid.co.uk/sectors/oil-content-and-oil-seed | 4 | 361
https://www.lipid.co.uk/news/rob-winwood-joins-consultant | 4 | 237
https://www.lipid.co.uk/news/another-successful-course-mylnefield-lipid-analysis | 4 | 62
https://www.lipid.co.uk/people/allan-dick | 4 | 28
https://www.lipid.co.uk/case-studies/omtrygtm-analysis-api-fpp | 3 | 3942
https://www.lipid.co.uk/sectors/clinical-samples | 3 | 196
https://www.lipid.co.uk/news/mla-team-scores-perfect-zero-latest-proficiency-testing-cannabis-and-related-products | 3 | 128
https://www.lipid.co.uk/services/stability | 2 | 2478
https://www.lipid.co.uk/news/25-years-our-story-so-far | 2 | 302
https://www.lipid.co.uk/services/method-development-validation | 2 | 201
https://www.lipid.co.uk/sectors/biofuel-analysis | 2 | 160
https://www.lipid.co.uk/news/wishing-sheena-happy-retirement | 2 | 49
https://www.lipid.co.uk/news/analytical-chemist-vacancy-1 | 2 | 27
https://www.lipid.co.uk/news/rob-winwood-can-sterols-and-stanols-be-beneficial-heart-health-and-how-do-i-find-out-how-much | 1 | 3022
https://www.lipid.co.uk/sectors | 1 | 444
https://www.lipid.co.uk/news/we-are-members-goed | 1 | 301
https://www.lipid.co.uk/quality | 1 | 287
https://www.lipid.co.uk/samples | 1 | 242
https://www.lipid.co.uk/news/research-article-encapsulated-fish-oil-products-available-uk-meet-regulatory-guidelines | 1 | 231
https://www.lipid.co.uk/news/issfal-issues-new-guidelines-analysis-blood-status-clinical-research | 1 | 170
https://www.lipid.co.uk/sectors/nutraceuticals | 1 | 161
https://www.lipid.co.uk/news/gmp-stability-storage-and-testing | 1 | 158
https://www.lipid.co.uk/videos | 1 | 85
https://www.lipid.co.uk/news/meet-our-newest-team-members | 1 | 63
https://www.lipid.co.uk/news/dietary-high-oleic-acid-soybean-oil-dose-dependently-attenuates-egg-yolk-content-n-3 | 1 | 60
https://www.lipid.co.uk/services/lipid-analysis/meet-team | 1 | 48
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-10/Sample Submission Form Oct 2018.pdf | 1 | 23
https://www.lipid.co.uk/people/dr-gary-dobson | 1 | 12
https://www.lipid.co.uk/register-fatty-acids-lipids-analysis-course | 1 | 11
https://www.lipid.co.uk/people/julie-sungurtas | 1 | 11
https://www.lipid.co.uk/news/eu-amendments-heavy-metals-go-effect | 0 | 7519
https://www.lipid.co.uk/news/thought-provoking-paper-bmj-potential-effect-food-emulsifiers-cardiovascular-diseases-cvd | 0 | 1621
https://www.lipid.co.uk/sectors/skin-lipids-and-skin-health | 0 | 257
https://www.lipid.co.uk/news | 0 | 256
https://www.lipid.co.uk/news/cannabidiol-safe-daily-dose-limit-cut-food-regulator | 0 | 248
https://www.lipid.co.uk/sectors/food-drink | 0 | 144
https://www.lipid.co.uk/about-website | 0 | 95
https://www.lipid.co.uk/people/stuart-ramage | 0 | 61
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-10/GMP 34058 120515 Veterinary.pdf | 0 | 60
https://www.lipid.co.uk/news/new-anti-inflammatory-product-created-following-analysis-mylnefield-lipid-analysis | 0 | 58
https://www.lipid.co.uk/news/mylnefield-lipid-analysis-claims-first-place-prestigious-proficiency-testing-programme | 0 | 48
https://www.lipid.co.uk/people/dr-carol-ann-craig | 0 | 46
https://www.lipid.co.uk/events | 0 | 41
https://www.lipid.co.uk/useful-links | 0 | 39
https://www.lipid.co.uk/25th-anniversary-videos | 0 | 35
https://www.lipid.co.uk/people/professor-terry-k-smith | 0 | 31
https://www.lipid.co.uk/news?page=3 | 0 | 27
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-10/Customer Form Oct 2018.pdf | 0 | 24
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-10/GMP 34058 120515 Human.pdf | 0 | 23
https://www.lipid.co.uk/people/andrew-kindness | 0 | 21
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2018-10/JHL - Website Privacy Notice.FINAL_.V2.May2018.pdf | 0 | 21
https://www.lipid.co.uk/news?page=2 | 0 | 20
https://www.lipid.co.uk/news/new-study-shows-clear-benefit-increased-epa-dha-intake | 0 | 20
https://www.lipid.co.uk/user/login | 0 | 17
https://www.lipid.co.uk/people/claire-traynor | 0 | 16
https://www.lipid.co.uk/slides/rob-winwood-latest-blog | 0 | 9
https://www.lipid.co.uk/news/were-exhibiting-issfal-congress | 0 | 8
https://www.lipid.co.uk/slides/statement-graham-ogg | 0 | 6
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/inline-images/Mylnefield_Lipid_Analysis_Fish_Oil_Oxidisation_Process-100.jpg | 0 | 6
https://www.lipid.co.uk/news/important-information-regarding-prices-1st-april-2021 | 0 | 5
https://www.lipid.co.uk/cookie-policy | 0 | 5
https://www.lipid.co.uk/slides/latest-blog-egg-centric-nutrition-humans | 0 | 5
https://www.lipid.co.uk/new-customer-form | 0 | 5
https://www.lipid.co.uk/people/charlie-scrimgeour | 0 | 4
https://www.lipid.co.uk/news/reduce-it-study | 0 | 3
https://www.lipid.co.uk/freedom-information | 0 | 3
https://www.lipid.co.uk/news/scotlands-life-sciences-awards-2019-call-nominations-now-open | 0 | 2
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/styles/flexslider_full_scale_and_crop_1663_550/public/2023-08/mla_cannabinoid_analysis.jpg?itok=KhJwyxHH | 0 | 2
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/styles/flexslider_full_scale_and_crop_1663_550/public/2025-01/chemist-2815640_1920_0.jpg?itok=AmmJeVrx | 0 | 2
https://www.lipid.co.uk/analytical/ | 0 | 1
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2023-09/Mylnefield_Lipid_Analysis_Oxidised_Fish_Oils_web.jpg | 0 | 1
https://www.lipid.co.uk/events/webinar-lipid-classes-compounds-quality-control-and-contaminants | 0 | 1
https://www.lipid.co.uk/news/goed-study-puts-rest-toxicity-concerns | 0 | 1
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/styles/feature_block/public/2021-12/GOED Logo Feature Box Size_0.jpg?itok=bGtvoquT | 0 | 1
https://www.lipid.co.uk/slides/we-are-members-goed | 0 | 1
https://www.lipid.co.uk/FOIPolicy | 0 | 1
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/styles/carousel_image/public/2018-10/GC Vials compressed.jpg?itok=d4AN6hUh | 0 | 1
https://www.lipid.co.uk/news?page=1 | 0 | 1
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/styles/flexslider_full_scale_and_crop_1663_550/public/2018-10/Shaking Oil Compressed_0.jpg?itok=rL23IQKN | 0 | 1
https://www.lipid.co.uk/sites/www.lipid.co.uk/files/2025-01/GOED cert image.jpg | 0 | 1

## GA4
Page path | Views (12m) | Active users
/ | 2698 | 2279
/services | 372 | 255
/news | 276 | 262
/about-us | 274 | 205
/services/analyses | 227 | 153
/contact-us | 224 | 167
/sectors | 211 | 126
/new-customer-form | 176 | 70
/quality | 137 | 96
/samples | 118 | 96
/bill-christie-0 | 106 | 71
/news/oxidised-fish-oil-problem | 100 | 92
/services/training-course | 76 | 56
/bill-christie | 73 | 59
/news/egg-centric-nutrition-humans | 73 | 63
/testimonials | 73 | 66
/404.html | 71 | 62
/james-hutton-limited | 67 | 60
/sectors/clinical-samples | 66 | 56
/services/method-development-validation | 65 | 56
/services/lipid-analysis/meet-team | 62 | 30
/search/node | 61 | 38
/sectors/oil-content-and-oil-seed | 60 | 52
/sectors/food-drink | 55 | 48
/sectors/biofuel-analysis | 54 | 44
/white-papers/white-paper-1 | 49 | 46
/sectors/nutraceuticals | 48 | 40
/sectors/skin-lipids-and-skin-health | 47 | 43
/useful-links | 46 | 45
/403.html | 45 | 40
/news/eu-amendments-heavy-metals-go-effect | 38 | 36
/case-studies/omtrygtm-analysis-api-fpp | 37 | 36
/user/login | 34 | 22
/news/mla-team-scores-perfect-zero-latest-proficiency-testing-cannabis-and-related-products | 33 | 30
/form/contact/confirmation | 32 | 29
/news/oxidised-fish | 31 | 31
/services/stability | 31 | 29
/news/professor-frank-d-gunstone | 28 | 22
/about-website | 27 | 27
/news/cannabidiol-safe-daily-dose-limit-cut-food-regulator | 27 | 28
/cookie-policy | 26 | 26
/events | 26 | 22
/claire-traynor | 25 | 22
/charlie-scrimgeour | 21 | 21
/news/mylnefield-lipid-analysis-claims-first-place-prestigious-proficiency-testing-programme | 21 | 19
/news/residual-solvents-analysis | 21 | 21
/news/rob-winwood-joins-consultant | 18 | 18
/news/statement-graham-ogg-0 | 17 | 17
/news/thought-provoking-paper-bmj-potential-effect-food-emulsifiers-cardiovascular-diseases-cvd | 17 | 17
/news/heavy-metal-analysis-icp-ms | 16 | 16
/news/mylnefield-lipid-analysis-work-study-characterising-ratfish-liver-oil | 16 | 15
/news/we-are-members-goed | 16 | 16
/node/761 | 16 | 16
/user/194 | 15 | 1
/news/important-information-regarding-prices-1st-april-2021 | 14 | 14
/news/omega-3-fatty-acid-content-should-be-expressed-weight-not-area-percent-says-goed-industry | 14 | 14
/news/meet-team-claire-traynor-celebrating-25-years | 12 | 9
/news/new-database-msu-references-450-plant-fatty-acids | 12 | 10
/people/allan-dick | 12 | 9
/node/604 | 11 | 11
/user/1 | 11 | 1
/news/25-years-our-story-so-far | 10 | 9
/news/meet-our-newest-team-members | 9 | 9
/news/rob-winwood-can-sterols-and-stanols-be-beneficial-heart-health-and-how-do-i-find-out-how-much | 9 | 9
/people/dr-rob-winwood | 9 | 5
/contact.asp | 8 | 8
/news/dietary-high-oleic-acid-soybean-oil-dose-dependently-attenuates-egg-yolk-content-n-3 | 8 | 8
/news/issfal-issues-new-guidelines-analysis-blood-status-clinical-research | 8 | 8
/2021/includes/popups/expo/expoAssetTracking.asp | 7 | 7
/news/another-successful-course-mylnefield-lipid-analysis | 7 | 7
/news/gmp-stability-storage-and-testing | 7 | 7
/news/new-anti-inflammatory-product-created-following-analysis-mylnefield-lipid-analysis | 7 | 7
/news/research-article-encapsulated-fish-oil-products-available-uk-meet-regulatory-guidelines | 5 | 5
/news/were-exhibiting-issfal-congress | 5 | 5
/people/claire-traynor | 5 | 1
//checkout/ | 4 | 4
/news/analytical-chemist-vacancy-1 | 4 | 5
/news/new-paper-first-report-quality-and-purity-evaluations-avocado-oil-sold-us | 4 | 4
/news/node/604 | 4 | 4
/sectors/node/757 | 4 | 4
/services/node/757 | 4 | 4
/25th-anniversary-videos | 3 | 3
/case-studies | 3 | 3
/case-studies/node/604 | 3 | 3
/case-studies/node/761 | 3 | 3
/news/goed-study-puts-rest-toxicity-concerns | 3 | 3
/news/open-business | 3 | 3
/news/scotlands-life-sciences-awards-2019-call-nominations-now-open | 3 | 3
/news/wishing-sheena-happy-retirement | 3 | 3
/people/demi-elliot | 3 | 1
/register-fatty-acids-lipids-analysis-course | 3 | 3
/sectors/node/604 | 3 | 3
/case-studies/node/757 | 2 | 2
/media/add/image | 2 | 1
/news/new-study-shows-clear-benefit-increased-epa-dha-intake | 2 | 2
/news/node/757 | 2 | 2
/news/reduce-it-study | 2 | 2
/node/623 | 2 | 1
/node/757 | 2 | 2
/node/node/604 | 2 | 2
/sectors/node/761 | 2 | 2
/services/node/604 | 2 | 2
/services/node/761 | 2 | 2
/slides/mylnefield-lipid-analysis | 2 | 1
/user/password | 2 | 2
/videos | 2 | 2
/events/webinar-lipid-classes-compounds-quality-control-and-contaminants | 1 | 1
/filter/tips | 1 | 1
/media/add | 1 | 1
/news/node/761 | 1 | 1
/node | 1 | 1
/node/658 | 1 | 1
/node/node/757 | 1 | 1
/node/node/761 | 1 | 1
/people/christine-branney | 1 | 1
/people/dr-gary-dobson | 1 | 1
/people/finlay-stewart | 1 | 1
/people/lucy-asare | 1 | 1
/people/professor-terry-k-smith | 1 | 1
/people/sophie-craig | 1 | 1
/samplesubmission | 1 | 1
/subscribe | 1 | 1